Actions Arising from Preliminary Meeting of Hoveton Neighbourhood Plan Steering Group

HVH, Jubilee Room

28th March 2024

Present: -

Cllr Kerry Walker (KW), Cllr Barry Edwards (BE), Ann-marie Watton (A-MW), Mick Watton (MW), Greg Slater(GS), Cllr Russell Reeve (RR), Geoff Cook (GC), Ben Bethel (BB), Garry Walker (GW)

Apologies: -

Barbara Clements (BC), Cllr Richard Stowe (RS)

Actions in order of Agenda Item: -

- Matter for HCC, suggested edits for Steering Group are: -

  - Add to ToR requirement for a liaison point of contact with Wroxham Parish Council.

  - Delete fist paragraph, third page due to conflict with bullet point 4 first page.

- Due Diligence

  - Review alternative consultants to Rachel Leggett with a view to seeking comparative quotes for Neighbourhood Plan support.  (RR)

  - Draft generic scope of work for use in obtaining quotations. (GW)/(GS)

- Review Locality Funding website on regular basis for opening of funding window. (RS)

- Stakeholders

  - Gather list of stakeholders and send to KW. (All)

  - Start Stakeholder Register. (KW)

  - Ask Wroxham Parish Council to share their Stakeholder Register. (KW)

- Neighbourhood Plan Familiarisation

  - Arrange a meeting with Wroxham Parish Council to discuss their Neighbourhood Plan scope and experience. (KW)

  - Arrange for a representative from Lingwood and Burlingham Community Council to discuss their Neighbourhood Plan experience. (BB)

  - Review selection of Neighbourhood Plans to gain greater familiarity with the structure and content. (All)

- Community Documentation

  - Carry out a document search for material relating to Hoveton. (KW)

  - Set up document storage Google drive. (GW)

- Steering Group Membership & Operation

  - Seek new members for the Steering Group to bring the number up to 12 and reach across a broader cross-section of the community.  Draft article for New Bridge magazine to support this effort. (BB)/(KW)

  - Send out copy of presentation to SG members. (KW)

  - Send out calendar of proposed meeting dates. (BB)

  - Selection of Steering Group roles deferred to a future meeting.