Minutes of Meeting of Hoveton Neighbourhood Plan Steering Group
Via Zoom
1st May 2025

Present: -
Ann-Marie Watton (A-MW), Mick Watton (MW), Garry Walker (GW), Kerry Walker (KW), Cllr Richard Stowe (RS), Cllr Russell Reeve (RR), Louise Cornell (LC)

Apologies: -
Greg Slater (GS), Kelvin Dore (KD), Peter Mantle, Ben Bethel (BB), Barbara Clements (BC), Kate Williams (KHW)

Note:  This meeting was originally scheduled for 23rd April but due to technical difficulties with the video conferencing equipment the meeting was abandoned and rescheduled for the following week.

1.  Minutes of Last Meeting 

The minutes of the last meeting, (27th March) were accepted.

2. Appointment of New Chair

Due to the resignation of Geoff Cook, it was necessary to appoint a new Chair.  Richard Stowe accepted the nomination and was appointed Chair of the Steering Group.  Ann-Marie Watton agreed to be Vice Chair.

It was agreed that RS would contact Geoff to thank him for his contribution to the Steering Group over the period he was Chair.

Action: RS to contact GC

3. Non-Designated Heritage Assets Report

The Non-Designated Heritage Asset (NDHA) report has been completed.  LC commented that it was one of the best examples she had seen.  It was agreed to accept the report.  Some discussion was had on the next steps with the information, for example, should we inform the owners of the properties that they are included in the report.  It was agreed to discuss this further at the next meeting.

[bookmark: _GoBack]Action: Heritage Asset Report to be included on the agenda for the May meeting

4. Site Assessment Work

LC advised that this work is progressing well and was 80% completed.
 
5. Draft Neighbourhood Plan

LC advised that she has incorporated most of the comments she has received.

The meeting then stepped through the draft plan discussing comments that had been made.  The following points were made: -

It was agreed that we needed a specific objective on climate change.

The draft plan mentions younger members of the community but not to a great extent.  LC agreed to rework the Vision Statement giving more emphasis to provisions for younger people.

Policy numbering needs to be change to avoid confusion with NNDC numbering, HNPX rather than HOVX.

It was asked if we could enforce the adoption of roads in the village, this cannot be done.

With regard to issues of grey field and brown field sites, there was a discussion whether the village centre should be zoned to differentiate the various parts. LC advised that grey field sites related only to areas close to green belt. Consequently, as Norfolk does not have any greenbelt, any zoning would be of brownfield sites.

 The zones would be: -

1. From Kings Head Courtyard and cottages, Waterside rooms to the car park next to Minor and Brady estate agent’s office.
2. Roy’s Medium Stay Car Park.
3. Roy’s Coach Park.
4. Granary Staithe
5. River frontage adjacent to Granary Staithe and the village precinct.  

It was agreed that each of these zones would be covered individually and a policy will be developed.

Action : LC to add zones to new village map. If any problems with boundaries LC will contact KW.

It was noted that the Broads Authority had still not provided the map files.  LC will follow-up with BB and Broads Authority.

Action : LC to contact Natalie Beal regarding map files.

The amount of area devoted to car parks was discussed and despite there being large car parks, in the summer months they were often full.  It was noted that NNDC have designated the car park land for retail expansion in their Local Plan.

More work is needed on the provision of local facilities.  The potential for cultural/art facilities and a market was discussed.  It was also noted that Wroxham Barns, Bewilderwood and Hoveton Hall lay in the parish and should be referred to in the Neighbourhood Plan.  Some discussion was had on the role of the village hall and sports field.  It was also commented that more could be made of the riverside, including better access.

Traffic was discussed and LC asked if there was much data.  KW said she would provide the latest available SAM2 data.

Action: KEW to collect SAM2 data and provide to CCP

With regard to the natural environment, it was agreed we need a biodiversity policy.  LC asked if there was a green corridor that passes through the centre of the settlement.  The green corridor map was reviewed and showed green corridors in the centre.

LC will circulate the next draft of the Neighbourhood Plan in the next week or so.

Action: LC to revise and distribute latest update of the draft Neighbourhood Plan 

6. AoB

None

End of Meeting
 

Next Meeting Date: 22nd May 2025 7:00pm, HVH Jubilee Room and Zoom

